## Data Entry sheet Sikkim
DPR Projects Invoice Status Sheet
A.
Contract Agreement details | Project Name |  |  | Sikkim Package | [5 empty] | Moraigaon | Factor Based
| No. of Stretches |  |  | 5 | [5 empty] | 1
| Name of stretches |  |  | Package 1 | Package 2 | Package 3 | Package 4 | Package 5 |  | Moraigaon
| Length, km OR Factor (%) |  |  | 13.9 | 22 | 15.4 | 20.1 | 28.6
| Total Project Length, km. |  |  | 100
| Project cost |  |  | 7962170.2 | 12601996 | 8821397.2 | 11513641.8 | 16382594.8
| Contract Agreement Date |  |  | 2015-03-28
Contract Financial details | Key Personnel | [6 empty] | 15204000
| Support Professional | [6 empty] | 21369600
| Office Rent | [6 empty] | 100000
| Office Supplies | [6 empty] | 500000
| Furniture and Fixtures | [6 empty] | 200000
| Reports and Doc | [6 empty] | 1000000
| Survey & Investigations | [6 empty] | 19000000
| Misc Expenses | [6 empty] | 20000
| Post Report Consultation | [6 empty] | 160000
| Additional- Difference | [6 empty] | -271800
| Total Contract Value | [6 empty] | 57281800
Amendments | Revised Scope of Work |  |  | Package 1 | Package 2 | Package 3 | Package 4 | Package 5
| Amended length, km. |  |  | 23 | 40 | 120 | 50 | 90
| Stages compeleted before amendment |  |  | 2 | 2 | 2 | 2 | 2
| Payable Length, km. (after 10% variation as per Cl. 10 of CA) |  |  | 0 | 0 | 0 | 0 | 0
| Revised project cost as per payable length | [6 empty] | 0
3.4965
B. | Tax Invoice billing
|  | Name of stretches |  | Package 1 | Package 2 | Package 3 | Package 4 | Package 5 | Total
|  | Length, km. |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Project Cost, Rs. |  | 7962170.2 | 12601996 | 8821397.2 | 11513641.8 | 16382594.8
Tax Invoice Billing | INVOICE Stage-1(Invoicing has to be linked with DAK management) | As per Agreement | Stage of Invoice |  | 3,4,5 |  | 3,4,5 | 3,4,5 |  | Select stages from the dropdown
|  |  | % age Payble for this Stage |  | 45% |  | 45% | 45% |  | add total of % payent fromStage master
|  |  | Amount Payable for this Stage | 0 | 5670898.2 | 0 | 5181138.81 | 7372167.66
|  |  | Completion days | 30 | 31 | 32 | 33 | 34 |  | Actual Days to Complete
|  |  | Target date | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01
|  | Invoice Detail | Payable Length | 21.61 | 22 | 118.46 | 20.1 | 28.6 |  | Length applicability to check'
|  |  | %age Claimed |  | 45% |  | 45% | 45%
|  |  | Invoice Amount (Submitted) | 0 | 5670898.2 | 0 | 5181138.81 | 7372167.66 | 18224204.67
|  |  | GST amount for Invoice | 0 | 1020761.676 | 0 | 932604.9858 | 1326990.1788 | inv no-
Invoice No/ Ref No.
|  |  | Date of Invoice | 2017-01-20 | 2017-01-20 | 2017-01-20 | 2017-01-20 | 2017-01-20 | 2017-01-20
|  | Invoice approval by Client | Invoice Amount (Approved) | [5 empty] | 18224204.67
|  |  | Corrected GST Amount (Approved) | [5 empty] | 2733630.7005
|  | Invoice Difference Analysis | Difference (Submitted-Approved) | [5 empty] | 0
|  |  | Is Difference acceptable | [5 empty] | Yes
If Not Then Disputed Amount
Correspondence on Disputed Amount
|  | Payment Receipt Against Invoice | Payment Received | [5 empty] | 18224204.67
|  |  | Date of Receipt | [5 empty] | 2018-05-23
|  | Payment Receipt Against Dispute | Amount Received
Dispute Reference
Date of Receipt
Total Out Standing Amount of Diputes till this Stage (after Payment)
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-1 Balance Amount in Case first is Submitted as partial | Second Invoice if Partial submitted previosly | Submitted Invoice Amount
GST amount for Invoice
|  | Invoice Detail | Invoice No
Date of Submission
|  |  | Invoice Amount (Submitted) | 698971 |  |  |  | 6989709
GST amount for Invoice
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Invoice Difference Analysis | Difference (Submitted-Approved)
Is Difference acceptable
If Not Then Disputed Amount
Correspondence on Disputed Amount
|  | Payment Receipt Against Invoice | Paid Amount Against Invoice
Date of Payment
|  | Payment Receipt Against GST | Received AmountAgainst GST
Date of Receipt Of GST Payment
|  | Payment Receipt Against Dispute | Amount Received
Dispute Reference
Date of Receipt
Total Out Standing Amount of Diputes till this Stage
Correspondence on Balance Disputed Amount
|  | Another Invoice if Partial submitted previosly | Submitted Invoice Amount
GST amount for Invoice
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-2 @ | As per Agreement | Stage of Invoice | 2 |  |  |  | 2
|  |  | % age Payble for this Stage | 5% |  |  |  | 5%
|  |  | Amount Payable for this Stage | 398108.51 |  |  |  | 819129.74
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 13.9 |  |  |  | 28.6 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 0 |  |  |  | 3494855
|  |  | GST amount for Invoice | 0 |  |  |  | 629073.9
|  |  | Invoice No/ Ref No. |  |  |  |  | 3-June,9306
|  |  | Date of Invoice |  |  |  |  | 2019-06-03
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Invoice Difference Analysis | Difference (Submitted-Approved)
Is Difference acceptable
If Not Then Disputed Amount
Correspondence on Disputed Amount
|  | Payment Receipt Against Invoice | Amount Received
Date of Receipt
|  | Payment Receipt Against GST | Amount Received
Date of Receipt
|  | Payment Receipt Against Dispute | Amount Received
Dispute Reference
Date of Receipt
Total Out Standing Amount of Diputes till this Stage
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-3 @ | As per Agreement | Stage of Invoice | 3 |  |  |  | 3
|  |  | % age Payble for this Stage | 5% |  |  |  | 5%
|  |  | Amount Payable for this Stage | 398108.51 |  |  |  | 819129.74
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) |  |  |  |  | 3494855
|  |  | GST amount for Invoice |  |  |  |  | 629073.9
Invoice No/ Ref No.
|  |  | Date of Invoice |  |  |  |  | 2018-11-03
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-4 @ | As per Agreement | Stage of Invoice | 4 |  |  |  | 4
|  |  | % age Payble for this Stage | 5% |  |  |  | 5%
|  |  | Amount Payable for this Stage | 398108.51 |  |  |  | 819129.74
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 0 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 28.6
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 0
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 0
Invoice No/ Ref No.
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | #REF! |  |  |  | #REF!
|  |  | Submitted amount |  |  |  |  | 3494855
|  |  | Date of Submission |  |  |  |  | 2018-06-21
|  |  | Received Amount |  |  |  |  | 87.14
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-5 @ |  |  | 2.5% |  |  |  | 2.5%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 199054.255 |  |  |  | 409564.87
|  |  | Submitted amount |  |  |  |  | 1747427
|  |  | Date of Submission |  |  |  |  | 2018-09-17
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-6 @ |  |  | 5% |  |  |  | 5%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 398108.51 |  |  |  | 819129.74
|  |  | Submitted amount |  |  |  |  | 2096913
|  |  | Date of Submission |  |  |  |  | 2019-02-26
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-7 @ |  |  | 10% |  |  |  | 10%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 796217.02 |  |  |  | 1638259.48
|  |  | Submitted amount |  |  |  |  | 6989709
|  |  | Date of Submission |  |  |  |  | 2019-06-10
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-8 @ |  |  | 5% |  |  |  | 5%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 398108.51 |  |  |  | 819129.74
|  |  | Submitted amount |  |  |  |  | 3494855
|  |  | Date of Submission |  |  |  |  | 2018-11-13
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-9 @ |  |  | 10% |  |  |  | 10%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 796217.02 |  |  |  | 1638259.48
|  |  | Submitted amount |  |  |  |  | 6989709
|  |  | Date of Submission |  |  |  |  | 2018-11-29
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-10 @ |  |  | 5% |  |  |  | 5%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 398108.51 |  |  |  | 819129.74
Submitted amount
Date of Submission
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-11 @ |  |  | 2.5% |  |  |  | 2.5%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 199054.255 |  |  |  | 409564.87
Submitted amount
Date of Submission
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-12@ |  |  | 10% |  |  |  | 10%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 796217.02 |  |  |  | 1638259.48
|  |  | Submitted amount |  |  |  |  | 6989709
|  |  | Date of Submission |  |  |  |  | 2019-05-10
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-13 @ |  |  | 10% |  |  |  | 10%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 796217.02 |  |  |  | 1638259.48
|  |  | Submitted amount |  |  |  |  | 3494854.5
3494854.5
|  |  | Date of Submission |  |  |  |  | 2019-02-25
2019-05-06
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-14 @ |  |  | 10% |  |  |  | 10%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 796217.02 |  |  |  | 1638259.48
|  |  | Submitted amount |  |  |  |  | 6989709
|  |  | Date of Submission |  |  |  |  | 2019-04-29
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-15 @ |  |  | 5% |  |  |  | 5%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 398108.51 |  |  |  | 819129.74
Submitted amount
Date of Submission
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-16 @ |  |  | 1% |  |  |  | 1%
|  | As per Agreement | Stage of Invoice | 1 |  |  |  | 1
|  |  | % age Payble for this Stage | 10% |  |  |  | 10%
|  |  | Amount Payable for this Stage | 796217.02 |  |  |  | 1638259.48
|  |  | Completion days | 30 |  |  |  | 30
|  |  | Target date | 2015-04-27 |  |  |  | 2015-04-27
|  | Invoice Detail | Payable Length | 21.61 |  |  |  | 87.14 |  |  | 0
|  |  | %age Claimed | 10% |  |  |  | 10%
|  |  | Invoice Amount (Submitted) | 1237859.698 |  |  |  | 4991536.052
|  |  | GST amount for Invoice | 222814.7456 |  |  |  | 898476.4894
|  |  | Invoice No/ Ref No. | Letter Stage-2 |  |  |  | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 |  |  |  | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 79621.702 |  |  |  | 163825.948
|  |  | Submitted amount |  |  |  |  | 163825.948
|  |  | Date of Submission |  |  |  |  | 2018-06-19
Received Amount
Date of Receipt/ Reminder
Time Taken
Formulas:
Sikkim Package = E9+[Sikkim Package, row above]
Package 2 = E9+[Package 2, row above]
Package 5 = E9+[Package 5, row above]

## Formats
Can be ontained from Bid-proposal-Header and Lines
Contract Summary |  |  | Amount |  |  | Stages Table
[6 empty] | Stage Code | Stage Description | Payment Terms | Total Contract Value | Package 1 | Package 2 | Package 3 | Package 4 | Package 5 | Addl-1 | Linked stage | Duration to Complete | Target Date
[7 empty] | Length, km OR Factor (%) |  | 100 | 13.9 | 22 | 15.4 | 20.1 | 28.6 | 12
3 Km
1 | Key Personnel & Sub prof | c | 15204000 | KP+SP |  | KD0 | Inception Report | 0% | 0 | [7 empty] | 15 | 2015-04-12
2 | Support Professional |  | 21369600 | SS |  | KD1 | On Submission of Draft feasibility | 15% | 8592270 | 1194325.53 | 1890299.4 | 1323209.58 | 1727046.27 | 2457389.22 | 429613.5 |  | 30 | 2015-04-27
3 | Office Rent |  | 100000 | RENT |  | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 5728180 | 796217.02 | 1260199.6 | 882139.72 | 1151364.18 | 1638259.48 | 286409 |  | 120 | 2015-07-26
4 | Office Supplies |  | 500000 | OFFSUP |  | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 5728180 | 796217.02 | 1260199.6 | 882139.72 | 1151364.18 | 1638259.48 | 286409 |  | 30 | 2015-04-27
5 | Furniture and Fixtures |  | 200000 | FURN |  | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 5728180 | 796217.02 | 1260199.6 | 882139.72 | 1151364.18 | 1638259.48 | 286409 |  | 150 | 2015-08-25
6 | Reports and Doc |  | 1000000 | REPORTS |  | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 25% | 14320450 | 1990542.55 | 3150499 | 2205349.3 | 2878410.45 | 4095648.7 | 716022.5 |  | 180 | 2015-09-24
7 | Survey & Investigations |  | 19000000 | SURVEY |  | KD6 | Final Feasibility cum preliminary design Report | 20% | 11456360 | 1592434.04 | 2520399.2 | 1764279.44 | 2302728.36 | 3276518.96 | 572818 |  | 240 | 2015-11-23
8 | Misc Expenses |  | 20000 | OTH |  | KD7 | Completion of Services including assistance during Bid Process | 10% | 5728180 | 796217.02 | 1260199.6 | 882139.72 | 1151364.18 | 1638259.48 | 286409 |  | 300 | 2016-01-22
10 | Post Report Consultation |  | 160000 | OTH |  |  |  |  | 57281800 | 7962170.2 | 12601996 | 8821397.2 | 11513641.8 | 16382594.8 | 2864090
11 | Additional- Difference |  | -271800 | OTH |  | KD8 | Additioanl Work - Pillar Work |  | 160000 | 0 | 160000 | 0 | 0 | 0 | In case of New Stretch EOT required
9 | Total |  | 57281800 |  |  | KD9 | Post Report Consultation |  | -271800 | 0 | 0 | -271800 | 0 | 0
12 | Additioanl Work - Pillar Work |  | 160000 | OTH |  | KD10 | Bonus 2% after 3A submission | [8 empty] | KD6 | 30 | 2015-12-23
13 | etc |  |  | OTH |  |  |  |  | 57170000
12 | Total Contract Value |  | 57281800 | 100%
[6 empty] | Ammendmends | Amended length, km. |  | 323 | 23 | 40 | 120 | 50 | 90
[7 empty] | Stages compeleted before amendment |  | 10 | 2 | 2 | 2 | 2 | 2 | EOT Date
| No of Packages |  | 5 |  |  |  | Payable Length, km. (after 10% variation as per Cl. 10 of CA) |  | 0 | 0 | 0 | 0 | 0 | 0
| Contract Agrement date |  | 2015-03-28 |  |  |  | Revised project cost as per payable length |  | 0 |  |  |  |  | 0
Package details for Invoice
[5 empty] | INV-01 |  |  |  |  | Package 1 | Package 2 | Package 3 | Package 4 | Package 5 | TOTAL
[6 empty] | Project Cost, Rs. |  |  |  | 7962170.2 | 12601996 | 8821397.2 | 11513641.8 | 16382594.8 | 57281800
| Input sheet for Project manager |  |  |  |  | As per Agreement | Stage of Invoice |  |  | 2 | 2 | 2 | 2 | 2 |  |  | Select stages from the dropdown
| vechiles, no, insurance | [5 empty] | % age Payble for this Stage |  |  | 15% | 15% | 15% | 15% | 15% |  |  | add total of % payment from Stage master |  | REPEATED
[7 empty] | Amount Payable for this Stage |  |  | 1194325.53 | 1890299.4 | 1323209.58 | 1727046.27 | 2457389.22 |  |  | calculation |  | REPEATED
[7 empty] | Completion days |  |  | 30 | 31 | 32 | 33 | 34 |  |  | Actual Days took to complete
[7 empty] | Target date | [9 empty] | Actual Completion Date
[7 empty] | Delayed/Ahead by |  |  | Target date-actual date | [6 empty] | Delay Difference to monitor
[6 empty] | Invoice Detail | Payable Length | [9 empty] | Logic to be defined / Manual
[7 empty] | %age Claimed |  |  | 15% | 15% | 15% | 15% | 15% |  |  | add total of % payment from Stage master
[7 empty] | Invoice Amount (Submitted) |  |  | 1194325.53 | 1890299.4 | 1323209.58 | 1727046.27 | 2457389.22 |  |  | calculation
Bill Summary
[5 empty] | A | Invoice Submitted | Invoice No | [7 empty] | INV-01 |  | Invoice Number
[7 empty] | Invoice Date | [7 empty] | 2016-12-05 |  | Inv submitted date
[7 empty] | Invoice Amount (Submitted) | [7 empty] | 8592270 |  | Calc
[7 empty] | GST / Tax percentage | [7 empty] | 15%
[7 empty] | GST Recived from Client | [7 empty] | 1288840.5 |  | Calc
[7 empty] | Gross BillAmount | [7 empty] | 9881110.5
[5 empty] | B | Invoice approval by Client | Invoice Amount (Approved) | [7 empty] | 8592270 |  | manual
[7 empty] | GST Recived from Client | [7 empty] | 15% |  | manual
[7 empty] | Less TDS | [7 empty] | 1288840.5
[7 empty] | Withheld Details | [7 empty] | 859227
With hold - Service Tax
[7 empty] | TDS on GST @ 2% | [7 empty] | 1288840.5
[7 empty] | Others | Project clearance
Alignment
Other
[7 empty] | Total With hold amount … | [7 empty] | 1288840.5
Release of Withheld Amount
[7 empty] | With hold - Service Tax | [7 empty] | 0
[7 empty] | TDS on GST @ 2% | [7 empty] | 0
[7 empty] | Others | Project clearance | [6 empty] | 0
[8 empty] | Alignment | [6 empty] | 0
[8 empty] | Other | [6 empty] | 0
[7 empty] | Total With hold amount Released… | [7 empty] | 0
[5 empty] | D | Payment Receipt | Amount Received | [7 empty] | 7733043
Date of Receipt
Total Received
[7 empty] | Cheque No / Online Ref | [7 empty] | RTGS ref/Cheq
[7 empty] | Date of Receipt | [7 empty] | 2018-05-23
[5 empty] | C | Invoice Difference Analysis | Difference (Submitted-Approved) | [7 empty] | 0 |  | Calc
[7 empty] | Is Difference acceptable | [7 empty] | Yes |  | Boolean
[7 empty] | If Not Then Disputed Amount | [9 empty] | Manual Amount
Total Out Standing Amount of Diputes till this Stage (after Payment)
Dispute Reference
[7 empty] | Correspondence on Disputed Amount | [7 empty] | File |  | File Attach
[6 empty] | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
Above are sample for the understanding
Formats as Deepakji explained yesterday can be used for user interface
Formulas:
Target Date = +D25+[Duration to Complete]
Target Date = +T14+[Duration to Complete]

## Report Format-1
DPR019 - Sikkim Projects (5 Packages) - NHIDCL
Contract Financial | [5 empty] | Stage Wise - Summary |  |  |  | Days to Complete | Target Date | 2016-12-05 | 2016-12-27 | 2017-01-20 | 2017-01-20 | 2017-06-01 | 2017-08-11 | 2017-09-11 | 2018-05-10 | 2018-03-16 | 2018-04-27 | 2018-04-26 | 2018-08-16 | 2019-02-20 | 2019-02-26 | Total | Balance Work
1 | Key Personnel |  |  |  | 15204000 |  | Inception Report | 0% | 0 | 7 | 2016-09-08 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
2 | Support Professional |  |  |  | 21369600 | KD1 | On Submission of Draft feasibility | 15% | 8592270 | 15 | 2016-09-16 | 8592270 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
3 | Office Rent |  |  |  | 100000 | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 5728180 | 45 | 2016-10-16 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882139.72 | 1151364.18 | 1260199.6 | #REF! | #REF!
4 | Office Supplies |  |  |  | 500000 | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 5728180 | 60 | 2016-10-31 | 0 | #REF! | 4049823.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882139.72 | 0 | 0 | #REF! | #REF!
5 | Furniture and Fixtures |  |  |  | 200000 | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 5728180 | 150 | 2017-01-29 | 0 | #REF! | 4049823.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882139.72 | 0 | 0 | #REF! | #REF!
6 | Reports and Doc |  |  |  | 1000000 | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 25% | 14320450 | 270 | 2017-05-29 | 0 | #REF! | 7246147.7 | 42884 | 0 | 0 | 0 | 0 | 0 | 0 | 2205349.3 | 0 | 0 | 0 | #REF! | #REF!
7 | Survey & Investigations |  |  |  | 19000000 | KD6 | Final Feasibility cum preliminary design Report | 20% | 11456360 | 270 | 2017-05-29 | 0 | #REF! | 0 | 0 | 270 | 3276518.96 | 0 | 0 | 0 | 2520399.2 | 0 | 0 | 0 | 0 | #REF! | #REF!
8 | Misc Expenses |  |  |  | 20000 | KD7 | Completion of Services including assistance during Bid Process | 10% | 5728180 | 300 | 2017-06-28 | 0 | #REF! | 0 | 0 | 0 | 0 | 1151364.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
9 | Total |  |  |  | 57393600 | KD8 | Additioanl Work - Pillar Work |  | 3396000 | 300 | 2017-06-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570650 | 1825350 | 0 | 0 | 0 | 0 | 0 | 3396000 | 0
10 | Post Report Consultation |  |  |  | 160000 | [20 empty] | 0 | 0
11 | Additional- Difference |  |  |  | -271800 | [20 empty] | 0 | 0
12 | Total Contract Value |  |  |  | 57281800 |  | Total Contract Value | 100% | 60677800 |  |  | 8592270 | #REF! | 15345794.22 | 42884 | 270 | 3276518.96 | 1151364.18 | 1570650 | 1825350 | 2520399.2 | 2205349.3 | 2646419.16 | 1151364.18 | 1260199.6 | #REF! | #REF!
|  | Mobilization date : | [5 empty] | A | Invoice Details |  |  | 8592270 | #REF! | 15345794.22 | 42884 | 270 | 3276518.96 | 1151364.18 | 1570650 | 1825350 | 2520399.2 | 2205349.3 | 2646419.16 | 1151364.18 | 1260199.6 | #REF!
[9 empty] | Allowed GST 18% |  |  | 1288840.5 | #REF! | 2301869.133 | 6432.6 | 0 | 589773.4128 | 207245.5524 | 282717 | 328563 | 453671.856 | 396962.874 | 476355.4488 | 207245.5524 | 226835.928 | #REF!
Kms | Division | Factor | Pkg Amount | Addl Work | Total |  |  |  | Total … |  |  | 9881110.5 | #REF! | 17647663.353 | 49316.6 | 270 | 3866292.3728 | 1358609.7324 | 1853367 | 2153913 | 2974071.056 | 2602312.174 | 3122774.6088 | 1358609.7324 | 1487035.528 | #REF!
Total Contract Amount
23 | Package 1 | 0.139 | 7962170.2 |  | 7962170.2 |  |  | B | Payment Details
230 | Package 2 | 0.22 | 12601996 |  | 12601996 |  |  |  | Invoice Amount |  |  | 8592270 | #REF! | 15345794.22 | 42884 | 270 | 3276518.96 | 1151364.18 | 1570650 | 1825350 | 2520399.2 | 2205349.3 | 2646419.16 | 1151364.18 | 1260199.6 | #REF!
| Package 3 | 0.154 | 8821397.2 |  | 8821397.2 |  |  |  | Less TDS |  |  | 859227 | #REF! | 1534579.422 | 4288.4 | 27 | 327651.896 | 115136.418 | 157065 | 182535 | 252039.92 | 220534.93 | 264641.916 | 115136.418 | 126019.96 | #REF!
| Package 4 | 0.201 | 11513641.8 | 1570650 | 13084291.8 |  |  |  | Receiveable |  |  | 9021883.5 | #REF! | 16113083.931 | 45028.2 | 243 | 3538640.4768 | 1243473.3144 | 1696302 | 1971378 | 2722031.136 | 2381777.244 | 2858132.6928 | 1243473.3144 | 1361015.568 | #REF!
| Package 5 | 0.286 | 16382594.8 | 1825350 | 18207944.8
253 | Total | 1 | 57281800 | 3396000 | 60677800 |  |  | C | Withhold Details
| Contract Date | 2016-09-01 | [6 empty] | Service Tax / GST Withheld |  |  | 1288840.5 | #REF! | 2301869.133 | 6432.6 | #REF! | 589773.4128 | 207245.5524 |  |  | 453671.856 |  |  |  |  | #REF!
[9 empty] | TDS on GST @ 2% | [11 empty] | 50408 |  |  |  |  | 50408
[9 empty] | SD | [16 empty] | 0
[9 empty] | Project clearance | [16 empty] | 0
[9 empty] | Alignment | [16 empty] | 0
[9 empty] | Other | [16 empty] | 0
[8 empty] | D | Total |  |  | 7733043 | #REF! | 13811214.798 | 38595.6 | #REF! | 2948867.064 | 1036227.762 | 1696302 | 1971378 | 2217951.28 | 2381777.244 | 2858132.6928 | 1243473.3144 | 1361015.568 | #REF!
Balance To Receive
[8 empty] | E | Payment Received |  |  |  | 13824103 | 16401784 | 2072455 | 5037647 |  | 3985095.2 |  | 3056400 | 2217951 |  |  |  |  | 46595435.2 | #REF!
[7 empty] | Stage of Invoice | % age Payble for this Stage | Amount Payable for this Stage | Completion days | Target date | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | Invoice Amount (Submitted) | total
Package/Stretch Wise - Details
[6 empty] | Package - P1 |  | 100% | 7962170.2 | Days |  | 2016-12-05 | 2016-12-27 | [12 empty] | Total | Balance Work
[7 empty] | Inception Report | 0% | 0 | 7 | 2016-09-08 | [14 empty] | 0 | 0
[6 empty] | KD1 | On Submission of Draft feasibility | 15% | 1194325.53 | 15 | 2016-09-16 | 1194325.53 | [13 empty] | 1194325.53 | 0
[6 empty] | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 796217.02 | 45 | 2016-10-16 |  | 796217.02 | [12 empty] | 796217.02 | 0
[6 empty] | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 796217.02 | 60 | 2016-10-31 |  | 796217.02 | [12 empty] | 796217.02 | 0
[6 empty] | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 796217.02 | 150 | 2017-01-29 |  | 796217.02 | [12 empty] | 796217.02 | 0
[6 empty] | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 25% | 1990542.55 | 270 | 2017-05-29 |  | 1990542.55 | [12 empty] | 1990542.55 | 0
[6 empty] | KD6 | Final Feasibility cum preliminary design Report | 20% | 1592434.04 | 270 | 2017-05-29 |  | 1592434.04 | [12 empty] | 1592434.04 | 0
[6 empty] | KD7 | Completion of Services including assistance during Bid Process | 10% | 796217.02 | 300 | 2017-06-28 |  | 796217.02 | [12 empty] | 796217.02 | 0
[6 empty] | KD8 | Additioanl Work - Pillar Work | 0% | 0 | 300 | 2017-06-28 | [14 empty] | 0 | 0
[7 empty] | TOTAL … |  |  |  |  | 1194325.53 | 6767844.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 7962170.2 | 0
|  | Mobilization date : | [5 empty] | A | Invoice Details |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Allowed GST 18% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kms | Division | Factor | Pkg Amount | Addl Work | Total |  |  |  | Total … |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Contract Amount
23 | Package 1 | 0.139 | 7962170.2 |  | 7962170.2 |  |  | B | Payment Details
230 | Package 2 | 0.22 | 12601996 |  | 12601996 |  |  |  | Invoice Amount |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Package 3 | 0.154 | 8821397.2 |  | 8821397.2 |  |  |  | Less TDS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Package 4 | 0.201 | 11513641.8 | 1570650 | 13084291.8 |  |  |  | Receiveable |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Package 5 | 0.286 | 16382594.8 | 1825350 | 18207944.8
253 | Total | 1 | 57281800 | 3396000 | 60677800 |  |  | C | Withhold Details
| Contract Date | 2016-09-01 | [6 empty] | Service Tax / GST Withheld |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | 0
[9 empty] | TDS on GST @ 2% | [11 empty] | 50408 |  |  |  |  | 50408
[9 empty] | SD | [16 empty] | 0
[9 empty] | Project clearance | [16 empty] | 0
[9 empty] | Alignment | [16 empty] | 0
[9 empty] | Other | [16 empty] | 0
[8 empty] | D | Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50408 | 0 | 0 | 0 | 0 | -50408
Balance To Receive
[8 empty] | E | Payment Received |  |  |  | 13824103 | 16401784 | 2072455 | 5037647 |  | 3985095.2 |  | 3056400 | 2217951 |  |  |  |  | 46595435.2 | -46595435.2
[6 empty] | Package - P2 |  | 100% | 12601996 |  |  | 2016-12-05 |  | 2017-01-20 | [6 empty] | 2018-04-27 |  |  |  | 2019-02-26 |  | Balance Work
[7 empty] | Inception Report | 0% | 0 | 7 | 2016-09-08 | [14 empty] | 0 | 0
[6 empty] | KD1 | On Submission of Draft feasibility | 15% | 1890299.4 | 15 | 2016-09-16 | 1890299.4 | [13 empty] | 1890299.4 | 0
[6 empty] | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 1260199.6 | 45 | 2016-10-16 | [13 empty] | 1260199.6 | 1260199.6 | 0
[6 empty] | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 1260199.6 | 60 | 2016-10-31 |  |  | 1260199.6 | [11 empty] | 1260199.6 | 0
[6 empty] | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 1260199.6 | 150 | 2017-01-29 |  |  | 1260199.6 | [11 empty] | 1260199.6 | 0
[6 empty] | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 25% | 3150499 | 270 | 2017-05-29 |  |  | 3150499 | [11 empty] | 3150499 | 0
[6 empty] | KD6 | Final Feasibility cum preliminary design Report | 20% | 2520399.2 | 270 | 2017-05-29 | [9 empty] | 2520399.2 |  |  |  |  | 2520399.2 | 0
[6 empty] | KD7 | Completion of Services including assistance during Bid Process | 10% | 1260199.6 | 300 | 2017-06-28 | [14 empty] | 0 | 1260199.6
[6 empty] | KD8 | Additioanl Work - Pillar Work | 0% | 0 | 300 | 2017-06-28 | [14 empty] | 0 | 0
[7 empty] | TOTAL … |  |  |  |  | 1890299.4 | 0 | 5670898.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2520399.2 | 0 |  |  | 1260199.6 | 11341796.4 | 1260199.6
2
[6 empty] | Package - P3 |  | 100% | 8821397.2 |  |  | 2016-12-05 | 2017-01-20 | [8 empty] | 2018-04-26 | 2018-08-16 |  |  |  | Balance Work
[7 empty] | Inception Report | 0% | 0 | 7 | 2016-09-08 | [14 empty] | 0 | 0
[6 empty] | KD1 | On Submission of Draft feasibility | 15% | 1323209.58 | 15 | 2016-09-16 | 1323209.58 | [13 empty] | 1323209.58 | 0
[6 empty] | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 882139.72 | 45 | 2016-10-16 | [11 empty] | 882139.72 |  |  | 882139.72 | 0
[6 empty] | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 882139.72 | 60 | 2016-10-31 |  | 882139.72 | [9 empty] | 882139.72 |  |  | 1764279.44 | -882139.72
[6 empty] | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 882139.72 | 150 | 2017-01-29 | [11 empty] | 882139.72 |  |  | 882139.72 | 0
[6 empty] | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 25% | 2205349.3 | 270 | 2017-05-29 | [10 empty] | 2205349.3 |  |  |  | 2205349.3 | 0
[6 empty] | KD6 | Final Feasibility cum preliminary design Report | 20% | 1764279.44 | 270 | 2017-05-29 | [14 empty] | 0 | 1764279.44
[6 empty] | KD7 | Completion of Services including assistance during Bid Process | 10% | 882139.72 | 300 | 2017-06-28 | [14 empty] | 0 | 882139.72
[6 empty] | KD8 | Additioanl Work - Pillar Work | 0% | 0 | 300 | 2017-06-28 | [14 empty] | 0 | 0
[7 empty] | TOTAL … |  |  |  |  | 1323209.58 | 882139.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2205349.3 |  |  | 0 | 7057117.76 | 1764279.44
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[6 empty] | Package - P4 |  | 100% | 11513641.8 |  | Target Date | 2016-12-05 | 2017-01-20 | 2017-01-20 | 2017-01-20 | 2017-05-31 |  | 2017-09-11 | 2018-05-10 |  |  |  |  | 2019-02-20 |  |  | Balance Work
[7 empty] | Inception Report | 0% | 0 | 7 | 2016-09-08 | [14 empty] | 0 | 0
[6 empty] | KD1 | On Submission of Draft feasibility | 15% | 1727046.27 | 15 | 2016-09-16 | 1: 1727046.27 | [6 empty] | 1727046.27 | 0
[6 empty] | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 1151364.18 | 45 | 2016-10-16 | [12 empty] | 1151364.18 |  | 1151364.18 | 0
[6 empty] | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 1151364.18 | 60 | 2016-10-31 | 2: 1151364.18 | [6 empty] | 1151364.18 | 0
[6 empty] | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 1151364.18 | 150 | 2017-01-29 | 3: 1151364.18 | [6 empty] | 1151364.18 | 0
[6 empty] | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 25% | 2878410.45 | 270 | 2017-05-29 | 4: 42884 | [6 empty] | 42884 | 2835526.45
[6 empty] | KD6 | Final Feasibility cum preliminary design Report | 20% | 2302728.36 | 270 | 2017-05-29 | 5: 270 | [6 empty] | 270 | 2302458.36
[6 empty] | KD7 | Completion of Services including assistance during Bid Process | 10% | 1151364.18 | 300 | 2017-06-28 | 7: 1151364.18 | [6 empty] | 1151364.18 | 0
[6 empty] | KD8 | Additioanl Work - Pillar Work |  | 1570650 | 300 | 2017-06-28 | 8: 1570650 | [6 empty] | 1570650 | 0
[7 empty] | TOTAL … |  |  |  |  | 1727046.27 | 0 | 1151364.18 | 42884 | 270 | 0 | 1151364.18 | 1570650 | 0 | 0 | 0 |  |  | 0 | 7946306.99 | 5137984.81
[6 empty] | Package - P5 |  | 100% | 16382594.8 |  |  | 1: 2016-12-05; 3: 2017-01-20; 6: 2017-08-11 | 2018-03-16 | [6 empty] | Balance Work
[7 empty] | Inception Report | 0% | 0 | 7 | 2016-09-08 | [14 empty] | 0 | 0
[6 empty] | KD1 | On Submission of Draft feasibility | 15% | 2457389.22 | 15 | 2016-09-16 | 1: 2457389.22 | [6 empty] | 2457389.22 | 0
[6 empty] | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 1638259.48 | 45 | 2016-10-16 | [14 empty] | 0 | 1638259.48
[6 empty] | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 1638259.48 | 60 | 2016-10-31 | 3: 1638259.48 | [6 empty] | 1638259.48 | 0
[6 empty] | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 1638259.48 | 150 | 2017-01-29 | 3: 1638259.48 | [6 empty] | 1638259.48 | 0
[6 empty] | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 25% | 4095648.7 | 270 | 2017-05-29 | 3: 4095648.7 | [6 empty] | 4095648.7 | 0
[6 empty] | KD6 | Final Feasibility cum preliminary design Report | 20% | 3276518.96 | 270 | 2017-05-29 | 6: 3276518.96 | [6 empty] | 3276518.96 | 0
[6 empty] | KD7 | Completion of Services including assistance during Bid Process | 10% | 1638259.48 | 300 | 2017-06-28 | [14 empty] | 0 | 1638259.48
[6 empty] | KD8 | Additioanl Work - Pillar Work |  | 1825350 | 300 | 2017-06-28 | [8 empty] | 1825350 | [5 empty] | 1825350 | 0
[7 empty] | TOTAL … |  |  |  |  | 2457389.22 | 0 | 7372167.66 | 0 | 0 | 3276518.96 | 0 | 0 | 1825350 | 0 | 0 |  |  | 0 | 14931425.84 | 3276518.96
Note on U108: Bill on Additional work for 849 Pillar on package - IV @ 1850 per pillar Total cost Rs. 15,70,650/- (Package - IV)
Note on V120: Bill on Additional work for 849 Pillar on package - IV @ 1850 per pillar Total cost Rs. 15,70,650/- (Package - V)

## Sheet2
56789043 | 230 Km | [5 empty] | 7893676.977 |  |  |  | DPR001-P01 | KD01 | On Submission of Draft feasibility
DPR001 | KD01 | 15% | 8518356.45 | DPR001-P01 | KD01 | 15% | 1184051.5466 |  |  |  | DPR001-P01 | KD02 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC)
| KD02 | 10% | 5678904.3 |  | KD02 | 10% | 789367.6977 | 789367.6977 |  |  | DPR001-P01 | KD03 | Final Feasibility cum preliminary design Report
| KD03 | 10% | 5678904.3 |  | KD03 | 10% | 789367.6977 |  | 789367.6977 |  | DPR001-P01 | KD04 | Completion of Services including assistance during Bid Process
| KD04 | 10% | 5678904.3 |  | KD04 | 10% | 789367.6977
| KD05 | 25% | 14197260.75 |  | KD05 | 25% | 1973419.2443
| KD06 | 20% | 11357808.6 |  | KD06 | 20% | 1578735.3954
| KD07 | 10% | 5678904.3 |  | KD07 | 10% | 789367.6977
| Bonus1 |  | 1419726.075 |  | Bonus1 | [5 empty] | DPR001-P02 | KD01 | On Submission of Draft feasibility
| Bonus2 |  | 1419726.075 |  | Bonus2 | [5 empty] | DPR001-P02 | KD02 | Report and Land Plan Schedules and Utility Relocation
|  |  | 58208769.075 | [7 empty] | DPR001-P02 | KD03 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs)
|  |  |  | DPR001-P02 | KD01 | 15% |  |  |  |  | DPR001-P02 | KD04 | Report on Envirnment and Social Impact Assessment
[5 empty] | KD02 | 10% |  |  |  |  | DPR001-P02 | KD05 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC)
[5 empty] | KD03 | 10% |  |  |  |  | DPR001-P02 | KD06 | Final Feasibility cum preliminary design Report
DPR001-P01 |  | 13.9 | 8091018.9014 |  | KD04 | 10% |  |  |  |  | DPR001-P02 | KD07 | Completion of Services including assistance during Bid Process
DPR001-P02 |  | 22 | 12805929.1965 |  | KD05 | 25% | [5 empty] | KD08
DPR001-P03 |  | 15.4 | 8964150.4376 |  | KD06 | 20%
DPR001-P04 |  | 20.1 | 11699962.5841 |  | KD07 | 10% |  | Project
DPR001-P05 |  | 28.6 | 16647707.9555 |  | Bonus1 |  |  |  | Summary
|  | 100 | 58208769.075 |  | Bonus2 |  |  |  | Biiling
|  |  |  | DPR001-P03 | [5 empty] | Packages
|  |  |  | DPR001-P04 | [6 empty] | Stage | this bill | Biiled
|  |  |  | DPR001-P05 | [6 empty] | P01-KD01 | 8% | 7%

## Sheet1
[7 empty] | Project | Package | Input
[9 empty] | NO | Date | Stage
Stages Table | [6 empty] | DPR001 | P3 | Inv-03 | 2019-08-02 | 4
| Stage Code | Stage Description | Payment Terms | Package 1 | Duration to Complete | Target Date |  | MB-03 |  | MB-04
|  | Length, km OR Factor (%) |  | 13.9 |  |  |  | P3 |  | P5
DPR001 | KD0 | Inception Report | 10% | 796217.02 | 15 | 2015-04-12
DPR001 | KD1 | On Submission of Draft feasibility | 10% | 796217.02 | 30 | 2015-04-27
DPR001 | KD2 | Report and Land Plan Schedules and Utility Relocation | 10% | 796217.02 | 120 | 2015-07-26
DPR001 | KD3 | Report and Indicative GAD of structures (bridges, grade separators, ROB/ROBs) | 10% | 796217.02 | 30 | 2015-04-27
DPR001 | KD4 | Report on Envirnment and Social Impact Assessment | 10% | 796217.02 | 150 | 2015-08-25 |  | 796217.02 |  | 1990542.55
DPR001 | KD5 | Draft Feasibility cum preliminary design Report and schedules to the Contract Agreement (EPC) | 20% | 1592434.04 | 180 | 2015-09-24
DPR001 | KD6 | Final Feasibility cum preliminary design Report | 20% | 1592434.04 | 240 | 2015-11-23
DPR001 | KD7 | Completion of Services including assistance during Bid Process | 10% | 796217.02 | 300 | 2016-01-22
DPR001 |  |  | 100% | 7962170.2 | [9 empty] | Stage
DPR001 | KD8 | Additioanl Work - Pillar Work |  | 0 | [5 empty] | 13 |  | invoice -05 | P01-MB01
DPR001 | KD9 | Post Report Consultation |  | 0 | [5 empty] | 12 |  |  | P01-MB02
DPR001 | KD10 | Bonus | 2% |  |  |  |  | 15924.3404 |  | 12 |  |  | P01-MB03
P01-MB04
[8 empty] | 812141.3604 |  | 1990579.55 |  |  | P01-MB05
P05-MB01
P05-MB02
P05-MB03
P05-MB04
P05-MB05

## Data Entry sheet-another sample
DPR Projects Invoice Status Sheet
A.
Contract Agreement details | Project Name |  |  | Consultancy services for Preparation of DPR for development of Economic Corridors, Inter corridors and Feeder routes to improve the effeciency of Freight Movement in India under Bharatmala Pariyojana (LOT-6/PKG-6) |  |  | Moraigaon
| No. of Stretches |  |  | 2 |  |  | 1
| Name of stretches |  |  | Satwari (Jammu Airport)-Kunjwani-Vijaypur | Gangheri in Pehowa-Charkhi Dadri-Narnaul |  | Moraigaon
| Length, km |  |  | 23 | 230
| Total Project Length, km. |  |  | 253
| Project cost |  |  | 6989709.2727 | 69897092.7273
| Contract Agreement Date |  |  | 2018-03-28
Contract Financial details | Key Personnel |  |  | 8820000
| Sub Professional |  |  | 9049189
| Support Professional |  |  | 869499
| Transportation |  |  | 720000
| Duty Travel |  |  | 427500
| Office Rent |  |  | 225000
| Office Supplies |  |  | 315000
| Furniture and Fixtures |  |  | 180000
| Reports and Doc |  |  | 10978750
| Survey & Investigations |  |  | 33083664
| Boundary Pillars |  |  | 4282200
| LA Team |  |  | 7936000
| Misc Expenses |  |  | 0
| Total Contract Value |  |  | 76886802
Amendments | Revised Scope of Work |  |  | Satwari (Jammu Airport)-Kunjwani-Vijaypur | Gangheri in Pehowa-Charkhi Dadri-Narnaul | Xyz | Moraigaon
| Amended length, km. |  |  | 30 | 207 | 0 | 0
| Stages compeleted before amendment |  |  | 2 | 3
| Payable Length, km. (after 10% variation as per Cl. 10 of CA) |  |  | 0 | 0 |  |  | 0
| Revised project cost as per payable length |  |  |  | 0 | 0 | 0
1.1
B. | Tax Invoice billing
|  | Name of stretches |  | Satwari (Jammu Airport)-Kunjwani-Vijaypur | Gangheri in Pehowa-Charkhi Dadri-Narnaul | Xyz
|  | Length, km. |  | 0 | 0 | 0
|  | Project Cost, Rs. |  | 6989709.2727 | 69897092.7273
Tax Invoice Billing | INVOICE Stage-1 (Invoicing has to be linked with DAK management) | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
Invoice No/ Ref No.
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Invoice Difference Analysis | Difference (Submitted-Approved)
Is Difference acceptable
If Not Then Disputed Amount
Correspondence on Disputed Amount
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Dispute | Amount Received
Dispute Reference
Date of Receipt
Total Out Standing Amount of Diputes till this Stage (after Payment)
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-1 Balance Amount in Case first is Submitted as partial | Second Invoice if Partial submitted previosly | Submitted Invoice Amount
GST amount for Invoice
|  | Invoice Detail | Invoice No
Date of Submission
|  |  | Invoice Amount (Submitted) | 698971 | 6989709
GST amount for Invoice
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Invoice Difference Analysis | Difference (Submitted-Approved)
Is Difference acceptable
If Not Then Disputed Amount
Correspondence on Disputed Amount
|  | Payment Receipt Against Invoice | Paid Amount Against Invoice
Date of Payment
|  | Payment Receipt Against GST | Received AmountAgainst GST
Date of Receipt Of GST Payment
|  | Payment Receipt Against Dispute | Amount Received
Dispute Reference
Date of Receipt
Total Out Standing Amount of Diputes till this Stage
Correspondence on Balance Disputed Amount
|  | Another Invoice if Partial submitted previosly | Submitted Invoice Amount
GST amount for Invoice
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-2 @ | As per Agreement | Stage of Invoice | 2 | 2
|  |  | % age Payble for this Stage | 5% | 5%
|  |  | Amount Payable for this Stage | 349485.4636 | 3494854.6364
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 23 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 0 | 3494855
|  |  | GST amount for Invoice | 0 | 629073.9
|  |  | Invoice No/ Ref No. |  | 3-June,9306
|  |  | Date of Invoice |  | 2019-06-03
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Invoice Difference Analysis | Difference (Submitted-Approved)
Is Difference acceptable
If Not Then Disputed Amount
Correspondence on Disputed Amount
|  | Payment Receipt Against Invoice | Amount Received
Date of Receipt
|  | Payment Receipt Against GST | Amount Received
Date of Receipt
|  | Payment Receipt Against Dispute | Amount Received
Dispute Reference
Date of Receipt
Total Out Standing Amount of Diputes till this Stage
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-3 @ | As per Agreement | Stage of Invoice | 3 | 3
|  |  | % age Payble for this Stage | 5% | 5%
|  |  | Amount Payable for this Stage | 349485.4636 | 3494854.6364
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) |  | 3494855
|  |  | GST amount for Invoice |  | 629073.9
Invoice No/ Ref No.
|  |  | Date of Invoice |  | 2018-11-03
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
| INVOICE Stage-4 @ | As per Agreement | Stage of Invoice | 4 | 4
|  |  | % age Payble for this Stage | 5% | 5%
|  |  | Amount Payable for this Stage | 349485.4636 | 3494854.6364
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 0 |  |  | 0
|  |  | %age Claimed | 10% | 230
|  |  | Invoice Amount (Submitted) | 841804.1168 | 0
|  |  | GST amount for Invoice | 151524.741 | 0
Invoice No/ Ref No.
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | #REF! | #REF!
|  |  | Submitted amount |  | 3494855
|  |  | Date of Submission |  | 2018-06-21
|  |  | Received Amount |  | 230
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-5 @ |  |  | 2.5% | 2.5%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 174742.7318 | 1747427.3182
|  |  | Submitted amount |  | 1747427
|  |  | Date of Submission |  | 2018-09-17
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-6 @ |  |  | 5% | 5%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 349485.4636 | 3494854.6364
|  |  | Submitted amount |  | 2096913
|  |  | Date of Submission |  | 2019-02-26
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-7 @ |  |  | 10% | 10%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 698970.9273 | 6989709.2727
|  |  | Submitted amount |  | 6989709
|  |  | Date of Submission |  | 2019-06-10
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-8 @ |  |  | 5% | 5%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 349485.4636 | 3494854.6364
|  |  | Submitted amount |  | 3494855
|  |  | Date of Submission |  | 2018-11-13
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-9 @ |  |  | 10% | 10%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 698970.9273 | 6989709.2727
|  |  | Submitted amount |  | 6989709
|  |  | Date of Submission |  | 2018-11-29
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-10 @ |  |  | 5% | 5%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 349485.4636 | 3494854.6364
Submitted amount
Date of Submission
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-11 @ |  |  | 2.5% | 2.5%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 174742.7318 | 1747427.3182
Submitted amount
Date of Submission
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-12@ |  |  | 10% | 10%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 698970.9273 | 6989709.2727
|  |  | Submitted amount |  | 6989709
|  |  | Date of Submission |  | 2019-05-10
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-13 @ |  |  | 10% | 10%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 698970.9273 | 6989709.2727
|  |  | Submitted amount |  | 3494854.5
3494854.5
|  |  | Date of Submission |  | 2019-02-25
2019-05-06
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-14 @ |  |  | 10% | 10%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 698970.9273 | 6989709.2727
|  |  | Submitted amount |  | 6989709
|  |  | Date of Submission |  | 2019-04-29
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-15 @ |  |  | 5% | 5%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 349485.4636 | 3494854.6364
Submitted amount
Date of Submission
Received Amount
Date of Receipt/ Reminder
Time Taken
| INVOICE Stage-16 @ |  |  | 1% | 1%
|  | As per Agreement | Stage of Invoice | 1 | 1
|  |  | % age Payble for this Stage | 10% | 10%
|  |  | Amount Payable for this Stage | 698970.9273 | 6989709.2727
|  |  | Completion days | 30 | 30
|  |  | Target date | 2018-04-27 | 2018-04-27
|  | Invoice Detail | Payable Length | 27.7 | 230 |  |  | 0
|  |  | %age Claimed | 10% | 10%
|  |  | Invoice Amount (Submitted) | 841804.1168 | 6989709.2727
|  |  | GST amount for Invoice | 151524.741 | 1258147.6691
|  |  | Invoice No/ Ref No. | Letter Stage-2 | SAICPL/EC/2018/DPR/Lot-6/Pkg-6/7398
|  |  | Date of Invoice | 2018-05-15 | 2018-05-15
|  | Invoice approval by Client | Invoice Amount (Approved)
Corrected GST Amount (Approved)
|  | Payment Receipt Against Invoice | Payment Received
Date of Receipt
|  | Payment Receipt Against Invoice (if Partially made) | Balance Amount (Received)
Date of Balance Payment
|  |  | Actual amount to be raised | 69897.0927 | 698970.9273
|  |  | Submitted amount |  | 698970.9273
|  |  | Date of Submission |  | 2018-06-19
Received Amount
Date of Receipt/ Reminder
Time Taken
Formulas:
Gangheri in Pehowa-Charkhi Dadri-Narnaul = E9+[Gangheri in Pehowa-Charkhi Dadri-Narnaul, row above]
Letter Stage-2 = E9+[Letter Stage-2, row above]